## MB 654 (hidden)
Name of work |  | : | Construction of Permanent approach bridge and road from ECR to Indian Maritime University (IMU) Chennai -600010.
Agreement No. |  | : | 17/CE/CCDII/2012-13
Agency |  | : | M/s.Copco Engineering Private Limited, Chennai
eighth of this bill |  | : | Tenth RA Bill
Date of Commencement work |  | : | 23.11.2012
Date of actual completion of work |  | : | Work - in - Progress
Date of Measurements: 27.01.2014
Item No | Details of Actual measurements/ Particulars | Number |  | Length | Width | Depth | Qty
1.18 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
| Pier Piles ( P1/4) (7.59 -(1.57+3.63) =2.39 | 3.14 x1.2 x2.39x47.10 |  |  |  |  | 424.16
|  | 1 x 3.14 x 1.2 x0.30 x 47.10 |  |  |  |  | 53.2418
| C/0 Page 38 of CMB 654 |  |  |  |  | Total | 477.4018
Date of Measurements: 27.01.2014
Item No | Details of Actual measurments/ Particulars | Number |  | Length | Width | Depth | Qty
1.07 | Providing & placing in position at all depths and heights High - yield strength steel Fe 415 grade reinforcement bars including cutting, straightening, bending, binding with PVC coated G.I. annealed binding wire of 18 SWG, testing of materials complete.
1. Pile work (46)
1 | Pier Piles ( P1/6) | Nos |  | M | 10mm Dia | 16mm Dia | 32mm Dia
| Main Rod 32mm Dia Vle | 1 | 24 | 16.15 | - | - | 387.6
| Main Rod 32mm Dia Vle | 1 | 8 | 13.85 | - | - | 110.8
| Laps 32 mm Dia | 1 | 32 | 1.98 | - | - | 63.36
| Inner Ring 16mm Dia | 1 | 16 | 3.35 | - | 53.6 | -
| Stiffner Ring 16mm Dia | 1 | 4 | 0.98 | - | 3.92 | -
| Hook for lowering cage 16mm Dia | 1 | 1 | 1 |  | 1
| Outer Helical ties 10mm Dia | 1 | 27 | 12.2 | 329.4 | - | -
[5 empty] | 329.4 | 58.52 | 561.76
[5 empty] | M | M | M
| 32 mm Dia |  | 561.76 M @ 6.31 kg /m = 3544.706 |  |  |  | 3544.7056
| 16 mm Dia |  | 58.52 M @ 1.58 kg/m = 92.462 |  |  |  | 92.4616
| 10 mm Dia |  | 329.4M @ .617 kg/m = 203.24 |  |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total (kgs) | 3840.407
1.08 | Extra for fusion bonded Epoxy coating of 220 micron thickness to Reinforced steel bars as per IS 13620-1993 (or the latest) from the approved firm as per section 1009.3 of MORTH specification and as directed by the Engineer -in-Charge.
UP TO 12 mm dia
| Pier Piles ( P1/6) Helical Ties 10mm dia | 27 | 12.2 | = 329.4 M @ .617 kg/ m |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 203.2398
16 & 20 mm dia
| Pier Piles ( P1/6) 16 mm dia inner Ring | 16 | 3.35 | = 53.60 M @ 1.58 kg/ m |  |  | 84.688
| Stiffner Ring 16mm Dia | 4 | 0.98 | = 3.92 M @ 1.58 kg/ m |  |  | 6.1936
| Hook for lowering cage 16mm Dia | 1 | 1 | = 1 M @ 1.58 kg/ m |  |  | 1.58
| C/0 Page 37 of CMB 654 |  |  |  |  | Total (kgs) | 92.4616
25 mm dia & Above
Pier Piles ( P1/6)
| Main Rod 32mm Dia Vle | 24 | 16.15 | 387.60 M @ 6.31 kg /m |  |  | 2445.756
| Main Rod 32mm Dia Vle | 8 | 13.85 | 110.80 M @ 6.31 kg /m |  |  | 699.148
| Laps 32 mm Dia | 32 | 1.98 | 63.36 M @ 6.31 kg /m |  |  | 399.8016
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 3544.7056
1.18 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
| Pier Piles ( P1/6) (7.59 -(1.36+3.63) =2.6 | 3.14 x1.2 x2.6 x 47.10kg |  |  |  |  | 461.4293
|  | 1 x 3.14 x 1.2 x0.30x 47.10 |  |  |  |  | 53.2418
| C/0 Page 38 of CMB 654 |  |  |  |  | Total(kgs) | 514.6711
Date of Measurements: 30.01.2014
Item No | Details of Actual measurments/ Particulars | Number |  | Length | Width | Depth | Qty
1.07 | Providing & placing in position at all depths and heights High - yield strength steel Fe 415 grade reinforcement bars including cutting, straightening, bending, binding with PVC coated G.I. annealed binding wire of 18 SWG, testing of materials complete.
1. Pile work (47)
1 | Pier Piles ( P1/5) | Nos |  | M | 10mm Dia | 16mm Dia | 32mm Dia
| Main Rod 32mm Dia Vle | 1 | 24 | 16.15 | - | - | 387.6
| Main Rod 32mm Dia Vle | 1 | 8 | 13.85 | - | - | 110.8
| Laps 32 mm Dia | 1 | 32 | 1.98 | - | - | 63.36
| Inner Ring 16mm Dia | 1 | 16 | 3.35 | - | 53.6 | -
| Stiffner Ring 16mm Dia | 1 | 4 | 0.98 | - | 3.92 | -
| Hook for lowering cage 16mm Dia | 1 | 1 | 1 |  | 1
| Outer Helical ties 10mm Dia | 1 | 27 | 12.2 | 329.4 | - | -
[5 empty] | 329.4 | 58.52 | 561.76
[5 empty] | M | M | M
| 32 mm Dia |  | 561.76 M @ 6.31 kg /m = 3544.706 |  |  |  | 3544.7056
| 16 mm Dia |  | 58.52 M @ 1.58 kg/m = 92.462 |  |  |  | 92.4616
| 10 mm Dia |  | 329.4 M @ .617 kg/m = 203.24 |  |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total (kgs) | 3840.407
1.08 | Extra for fusion bonded Epoxy coating of 220 micron thickness to Reinforced steel bars as per IS 13620-1993 (or the latest) from the approved firm as per section 1009.3 of MORTH specification and as directed by the Engineer -in-Charge.
UP TO 12 mm dia
| Pier Piles ( P1/5) Helical Ties 10mm dia | 27 | 12.2 | = 329.4 M @ .617 kg/ m |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 203.2398
16 & 20 mm dia
| Pier Piles ( P1/5) 16 mm dia inner ring | 16 | 3.35 | = 53.60 M @ 1.58 kg/ m |  |  | 84.688
| Stiffner Ring 16mm Dia | 4 | 0.98 | = 3.92 M @ 1.58 kg/ m |  |  | 6.1936
| Hook for lowering cage 16mm Dia | 1 | 1 | = 1 M @ 1.58 kg/ m |  |  | 1.58
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 92.4616
25 mm dia & Above
Pier Piles ( P1/5)
| Main Rod 32mm Dia Vle | 24 | 16.15 | 387.60 M @ 6.31 kg /m |  |  | 2445.756
| Main Rod 32mm Dia Vle | 8 | 13.85 | 110.80 M @ 6.31 kg /m |  |  | 699.148
| Laps 32 mm Dia | 32 | 1.98 | 63.36 M @ 6.31 kg /m |  |  | 399.8016
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 3544.7056
1.18 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
| Pier Piles (P1/5) 7.59-(1.71+3.63) = 2.25 | 3.14 x1.2 x2.25 x47.10kg |  |  |  |  | 399.3138
|  | 1 x 3.14 x 1.2 x0.30x47.10 |  |  |  |  | 53.2418
| C/0 Page 38 of CMB 654 |  |  |  |  | Total (kgs) | 452.5556
Date of Measurements: 30.01.2014
Item No | Details of Actual measurments/ Particulars | Number |  | Length | Width | Depth | Qty
1.07 | Providing & placing in position at all depths and heights High - yield strength steel Fe 415 grade reinforcement bars including cutting, straightening, bending, binding with PVC coated G.I. annealed binding wire of 18 SWG, testing of materials complete.
1. Pile work (48)
1 | Pier Piles ( P1/7) | Nos |  | M | 10mm Dia | 16mm Dia | 32mm Dia
| Main Rod 32mm Dia Vle | 1 | 24 | 16.15 | - | - | 387.6
| Main Rod 32mm Dia Vle | 1 | 8 | 13.85 | - | - | 110.8
| Laps 32 mm Dia | 1 | 32 | 1.98 | - | - | 63.36
| Inner Ring 16mm Dia | 1 | 16 | 3.35 | - | 53.6 | -
| Stiffner Ring 16mm Dia | 1 | 4 | 0.98 | - | 3.92 | -
| Hook for lowering cage 16mm Dia | 1 | 1 | 1 |  | 1
| Outer Helical ties 10mm Dia | 1 | 27 | 12.2 | 329.4 | - | -
[5 empty] | 329.4 | 58.52 | 561.76
[5 empty] | M | M | M
| 32 mm Dia |  | 561.76 M @ 6.31 kg /m = 3544.71 |  |  |  | 3544.7056
| 16 mm Dia |  | 58.52 M @ 1.58 kg/m = 92.462 |  |  |  | 92.4616
| 10 mm Dia |  | 329.4 M @ .617 kg/m = 203.24 |  |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total (kgs) | 3840.407
1.08 | Extra for fusion bonded Epoxy coating of 220 micron thickness to Reinforced steel bars as per IS 13620-1993 (or the latest) from the approved firm as per section 1009.3 of MORTH specification and as directed by the Engineer -in-Charge.
UP TO 12 mm dia
| Pier Piles ( P1/7) Helical Ties 10mm dia | 27 | 12.2 | = 329.4 M @ .617 kg/ m |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 203.2398
16 & 20 mm dia
| Pier Piles ( P1/7) 16mm dia inner ring | 16 | 3.35 | = 53.60 M @ 1.58 kg/ m |  |  | 84.688
| Stiffner Ring 16mm Dia | 4 | 0.98 | = 3.92 M @ 1.58 kg/ m |  |  | 6.1936
| Hook for lowering cage 16mm Dia | 1 | 1 | = 1 M @ 1.58 kg/ m |  |  | 1.58
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 92.4616
25 mm dia & Above
Pier Piles (P1/7)
| Main Rod 32mm Dia Vle | 24 | 16.15 | 387.6 M @ 6.31 kg /m |  |  | 2445.756
| Main Rod 32mm Dia Vle | 8 | 13.85 | 110.80M @ 6.31 kg /m |  |  | 699.148
| Laps 32 mm Dia | 32 | 1.98 | 63.36 M @ 6.31 kg /m |  |  | 399.8016
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 3544.7056
1.18 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
| Pier Piles ( P1/7) (7.59 -(1.83+3.63) = 2.13 | 3.14 x1.2 x2.13 x47.10kg |  |  |  |  | 378.0171
|  | 1 x 3.14 x 1.2 x0.30x47.10 |  |  |  |  | 53.2418
| C/0 Page 38 of CMB 654 |  |  |  |  | Total (kgs) | 431.2589
Date of Measurements: 03.02.2014
Item No | Details of Actual measurments/ Particulars | Number |  | Length | Width | Depth | Qty
1.07 | Providing & placing in position at all depths and heights High - yield strength steel Fe 415 grade reinforcement bars including cutting, straightening, bending, binding with PVC coated G.I. annealed binding wire of 18 SWG, testing of materials complete.
1. Pile work (49)
1 | Pier Piles ( P1/2) | Nos |  | M | 10mm Dia | 16mm Dia | 32mm Dia
| Main Rod 32mm Dia Vle | 1 | 24 | 16.1 | - | - | 386.4
| Main Rod 32mm Dia Vle | 1 | 8 | 13.8 | - | - | 110.4
| Laps 32 mm Dia | 1 | 32 | 1.98 | - | - | 63.36
| Inner Ring 16mm Dia | 1 | 16 | 3.35 | - | 53.6 | -
| Stiffner Ring 16mm Dia | 1 | 4 | 0.98 | - | 3.92 | -
| Hook for lowering cage 16mm Dia | 1 | 1 | 1 |  | 1
| Outer Helical ties 10mm Dia | 1 | 27 | 12.2 | 329.4 | - | -
[5 empty] | 329.4 | 58.52 | 560.16
[5 empty] | M | M | M
| 32 mm Dia |  | 560.16 M @ 6.31 kg /m = 3534.61 |  |  |  | 3534.6096
| 16 mm Dia |  | 58.52 M @ 1.58 kg/m = 92.462 |  |  |  | 92.4616
| 10 mm Dia |  | 329.4 M @ .617 kg/m = 203.24 |  |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total (kgs) | 3830.311
1.08 | Extra for fusion bonded Epoxy coating of 220 micron thickness to Reinforced steel bars as per IS 13620-1993 (or the latest) from the approved firm as per section 1009.3 of MORTH specification and as directed by the Engineer -in-Charge.
UP TO 12 mm dia
| Pier Piles (P1/2) Helical Ties 10mm dia | 27 | 12.2 | = 329.4 M @ .617 kg/ m |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 203.2398
16 & 20 mm dia
| Pier Piles (P1/2) 16 mm dia inner ring | 16 | 3.35 | = 53.60 M @ 1.58 kg/ m |  |  | 84.688
| Stiffner Ring 16mm Dia | 4 | 0.98 | = 3.92 M @ 1.58 kg/ m |  |  | 6.1936
| Hook for lowering cage 16mm Dia | 1 | 1 | = 1 M @ 1.58 kg/ m |  |  | 1.58
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 92.4616
25 mm dia & Above
Pier Piles ( P1/2)
| Main Rod 32mm Dia Vle | 24 | 16.1 | 386.4 M @ 6.31 kg /m |  |  | 2438.184
| Main Rod 32mm Dia Vle | 8 | 13.8 | 110.4 M @ 6.31 kg /m |  |  | 696.624
| Laps 32 mm Dia | 32 | 1.98 | 63.36 M @ 6.31 kg /m |  |  | 399.8016
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 3534.6096
1.18 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
| Pier Piles ( P1/2) 7.59 -(1.69+3.63) = 2.27 | 3.14 x1.2 x2.27 x 47.10kg |  |  |  |  | 402.8633
|  | 1 x 3.14 x 1.2 x0.30x47.10 |  |  |  |  | 53.2418
| C/0 Page 38 of CMB 654 |  |  |  |  | Total(kgs) | 456.1051
Date of Measurements: 03.02.2014
Item No | Details of Actual measurments/ Particulars | Number |  | Length | Width | Depth | Qty
1.07 | Providing & placing in position at all depths and heights High - yield strength steel Fe 415 grade reinforcement bars including cutting, straightening, bending, binding with PVC coated G.I. annealed binding wire of 18 SWG, testing of materials complete.
1. Pile work (50)
1 | Pier Piles ( P1/3) | Nos |  | M | 10mm Dia | 16mm Dia | 32mm Dia
| Main Rod 32mm Dia Vle | 1 | 24 | 16 | - | - | 384
| Main Rod 32mm Dia Vle | 1 | 8 | 13.7 | - | - | 109.6
| Laps 32 mm Dia | 1 | 32 | 1.98 | - | - | 63.36
| Inner Ring 16mm Dia | 1 | 16 | 3.35 | - | 53.6 | -
| Stiffner Ring 16mm Dia | 1 | 4 | 0.98 | - | 3.92 | -
| Hook for lowering cage 16mm Dia | 1 | 1 | 1 |  | 1
| Outer Helical ties 10mm Dia | 1 | 27 | 12.2 | 329.4 | - | -
[5 empty] | 329.4 | 58.52 | 556.96
[5 empty] | M | M | M
| 32 mm Dia |  | 556.96 M @ 6.31 kg /m = 3514.418 |  |  |  | 3514.4176
| 16 mm Dia |  | 58.52 M @ 1.58 kg/m = 92.462 |  |  |  | 92.4616
| 10 mm Dia |  | 329.4 M @ .617 kg/m = 203.24 |  |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total | 3810.119
1.08 | Extra for fusion bonded Epoxy coating of 220 micron thickness to Reinforced steel bars as per IS 13620-1993 (or the latest) from the approved firm as per section 1009.3 of MORTH specification and as directed by the Engineer -in-Charge.
UP TO 12 mm dia
| Pier Piles (P1/3) Helical Ties 10mm dia | 27 | 12.2 | = 329.4 M @ .617 kg/ m |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 203.2398
16 & 20 mm dia
| Pier Piles (P1/3) 16 mm dia inner ring | 16 | 3.35 | = 53.60 M @ 1.58 kg/ m |  |  | 84.688
| Stiffner Ring 16mm Dia | 4 | 0.98 | = 3.92 M @ 1.58 kg/ m |  |  | 6.1936
| Hook for lowering cage 16mm Dia | 1 | 1 | = 1 M @ 1.58 kg/ m |  |  | 1.58
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 92.4616
25 mm dia & Above
Pier Piles ( P1/3)
| Main Rod 32mm Dia Vle | 24 | 16 | 384 M @ 6.31 kg /m |  |  | 2423.04
| Main Rod 32mm Dia Vle | 8 | 13.7 | 109.6M @ 6.31 kg /m |  |  | 691.576
| Laps 32 mm Dia | 32 | 1.98 | 63.36 M @ 6.31 kg /m |  |  | 399.8016
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 3514.4176
1.18 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
| Pier Piles ( P1/3) 7.59 -(1.73+3.63) =2.23 | 3.14 x1.2 x2.23 x 47.10 |  |  |  |  | 395.7643
|  | 1 x 3.14 x 1.2 x0.30x47.10 |  |  |  |  | 53.2418
| C/0 Page 38 of CMB 654 |  |  |  |  | Total(kgs) | 449.0062
Date of Measurements: 05.02.2014
Item No | Details of Actual measurments/ Particulars | Number |  | Length | Width | Depth | Qty
1.07 | Providing & placing in position at all depths and heights High - yield strength steel Fe 415 grade reinforcement bars including cutting, straightening, bending, binding with PVC coated G.I. annealed binding wire of 18 SWG, testing of materials complete.
1. Pile work (51)
1 | Pier Piles ( P1/1) | Nos |  | M | 10mm Dia | 16mm Dia | 32mm Dia
| Main Rod 32mm Dia Vle | 1 | 24 | 16.2 | - | - | 388.8
| Main Rod 32mm Dia Vle | 1 | 8 | 13.9 | - | - | 111.2
| Laps 32 mm Dia | 1 | 32 | 1.98 | - | - | 63.36
| Inner Ring 16mm Dia | 1 | 16 | 3.35 | - | 53.6 | -
| Stiffner Ring 16mm Dia | 1 | 4 | 0.98 | - | 3.92 | -
| Hook for lowering cage 16mm Dia | 1 | 1 | 1 |  | 1
| Outer Helical ties 10mm Dia | 1 | 27 | 12.2 | 329.4 | - | -
[5 empty] | 329.4 | 58.52 | 563.36
[5 empty] | M | M | M
| 32 mm Dia |  | 563.36 M @ 6.31 kg /m = 3554.802 |  |  |  | 3554.8016
| 16 mm Dia |  | 58.52 M @ 1.58 kg/m = 92.462 |  |  |  | 92.4616
| 10 mm Dia |  | 329.4 M @ 617 kg/m = 203.24 |  |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total (kgs) | 3850.503
1.08 | Extra for fusion bonded Epoxy coating of 220 micron thickness to Reinforced steel bars as per IS 13620-1993 (or the latest) from the approved firm as per section 1009.3 of MORTH specification and as directed by the Engineer -in-Charge.
UP TO 12 mm dia
| Pier Piles ( P1/1) Helical Ties 10mm dia | 27 | 12.2 | = 317.2 M @ .617 kg/ m |  |  | 203.2398
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 203.2398
16 & 20 mm dia
| Pier Piles ( P1/1) 16 mm dia inner ring | 16 | 3.35 | = 53.60 M @ 1.58 kg/ m |  |  | 84.688
| Stiffner Ring 16mm Dia | 4 | 0.98 | = 3.92 M @ 1.58 kg/ m |  |  | 6.1936
| Hook for lowering cage 16mm Dia | 1 | 1 | = 1 M @ 1.58 kg/ m |  |  | 1.58
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 92.4616
25 mm dia & Above
Pier Piles ( P1/1)
| Main Rod 32mm Dia Vle | 24 | 16.2 | 388.8 M @ 6.31 kg /m |  |  | 2453.328
| Main Rod 32mm Dia Vle | 8 | 13.9 | 111.2 M @ 6.31 kg /m |  |  | 701.672
| Laps 32 mm Dia | 32 | 1.98 | 63.36 M @ 6.31 kg /m |  |  | 399.8016
| C/0 Page 37 of CMB 654 |  |  |  |  | Total(kgs) | 3554.8016
1.18 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
| Pier Piles ( P1/1) 7.59- (1.70+3.63) = 2.26 | 3.14 x1.2 x2.26 x47.10 kg |  |  |  |  | 401.0885
|  | 1 x 3.14 x 1.2 x0.30x47.10 |  |  |  |  | 53.2418
| C/0 Page 38 of CMB 654 |  |  |  |  | Total (kgs) | 454.3304
Epoxy Coating Abstract
1.08 | Extra for fusion bonded Epoxy coating of 220 micron thickness to Reinforced steel bars as per IS 13620-1993 (or the latest) from the approved firm as per section 1009.3 of MORTH specification and as directed by the Engineer -in-Charge.
S.No. | Date MB No/ Page No. | 10 mm |  | 16 mm | 32 mm | (in kgs) | Total in kgs
1 | 27.01.2014 654/CCSD3/II - Page 24 | #REF! |  | #REF! | #REF! |  | #REF!
2 | 27.01.2014 654/CCSD3/II - Page 25 | 203.2398 |  | 92.4616 | 3544.7056 |  | 3840.407
3 | 30.01.2014 654/CCSD3/II - Page 27 | 203.2398 |  | 92.4616 | 3544.7056 |  | 3840.407
4 | 30.01.2014 654/CCSD3/II - Page 29 | 203.2398 |  | 92.4616 | 3544.7056 |  | 3840.407
5 | 03.02.2014 654/CCSD3/II - Page 31 | 203.2398 |  | 92.4616 | 3534.6096 |  | 3830.311
6 | 03.02.2014 654/CCSD3/II - Page 33 | 203.2398 |  | 92.4616 | 3514.4176 |  | 3810.119
7 | 05.02.2014 654/CCSD3/II - Page 35 | 203.2398 |  | 92.4616 | 3554.8016 |  | 3850.503
| Total | #REF! |  | #REF! | #REF! |  | #REF!
[6 empty] | Say(MT) | #REF!
MS Plate Abstract
1.08 | Providing and driving inposition permanent MS liner using 6mm thick MS plate to the required depth for the 1200mm diameter Bored Cast in situ Piles directed by the Engineer-in-charge. (Rates including all charges for procurement, storage, transporation of MS plates, fabrication, erection, welding, bending, driving, cutting at the required level, including all labour, materials, plant and machinary handling etc. complete and as directed by the Engineer-in-charge. This item shall be operated where conditions differ from item no. 1.03 given above. This item is applicable for a depth beyond 5 mtr or where 'N' value is less than 15. The decision of Engineer-in-Charge is final in this matter.
S.No. | Date MB No/ Page No. | 6mm Plate |  |  |  | (in kgs) | Total in kgs
1 | 27.01.2014 654/CCSD3/II - Page 24 | 477.4018 |  |  |  |  | 477.4018
2 | 27.01.2014 654/CCSD3/II - Page 26 | 514.6711 |  |  |  |  | 514.6711
3 | 30.01.2014 654/CCSD3/II - Page 28 | 452.5556 |  |  |  |  | 452.5556
4 | 30.01.2014 654/CCSD3/II - Page 30 | 431.2589 |  |  |  |  | 431.2589
5 | 03.02.2014 654/CCSD3/II - Page 32 | 456.1051 |  |  |  |  | 456.1051
6 | 03.02.2014 654/CCSD3/II - Page 34 | 449.0062 |  |  |  |  | 449.0062
7 | 05.02.2014 654/CCSD3/II - Page 36 | 454.3304 |  |  |  |  | 454.3304
| Total | 3235.3291 |  |  |  |  | 3235.3291
[6 empty] | Say(MT) | 3.2353
100% Measurement were checked by me with draft copy of measurement and restricted the measurements as per the drawing wherever found more then the required measurements.
Junior Engineer,
CCSD 3/II, CPWD,
Chennai - 600006.
Above 50% measurements were checked by me along with draft copy.
Assistant Engineer,
CCSD 3/II, CPWD,
Chennai - 600006.
Above 10% measurements were checked by me along with draft copy.
Executive Engineer,
CCD .II, CPWD,
Chennai - 600006.

## MB -top page
CHENNAI PORT TRUST
CIVIL ENGINEERING DEPARTMENT
COMPUTERISED MEASUREMENT BOOK
DIVISION | :
SUB DIVISION | :
CMB No. | :
Pages | :
Bill No. & Period | :
Name of Work | :
Agreement No. | :
Contractor Name | :
Note: The proforma of Computerised Measurement book can be downloaded from ChPT official Web site www.chennaiport.gov.in

## MB - INS
INSTRUCTIONS
1. The measurement Book is the basis of all account of quantities whether of work done by contractor or by labour employed departmentally or of materials received and should be so kept that the transactions may be readily in the accounts of the department.
Measurement Books should be considered as very important account records and maintained very carefully and accurately as they may have to be produced evidence in a court of law.
2. All the books belonging to division should be numbered serially and Register should be maintained showing the serial number of each book the Sub-division to which issued, the date of issue and the date of its return, so that its eventual return to the Divisional Office may be watched.
A similar register should be maintained in the Sub-divisional office showing the names of the Sub-divisional and Sectional Officer to whom the Measurement Books have been issued Books have on longer in use should be withdrawn promptly even though not completely written up.
3. When an office or a sub-ordinate in executive charge of work or store is transferred, he should make over the Measurement Books issued to him to his successor and in the Register should be shown received back from the Relieved Officer and issued be Relieving Officer. The transfer should also be recorded after the last entry in each book and signed and dated by the Relieved and Relieving Officer or Subordinate.
1. Each set of Measurement should commence with entries starting:
(i) In the case of work done:-
(a) Full name of work as given in estimate
(b) Situation of work
(c) Name of contractor
(d) Number and date of his agreement
(e) Date of written order to commence work
(f) Date of actual completion of work
(g) Date of measurement
(h) Reference to previous mesasurment , if any
(i) Debit Head
(ii) In the case of bills for supply of materials
(a) Name of supplier:
(b) Number and date of his agreement or order
(c) Purpose of supply in one of the following forms applicable to the case.
(i) Stock for all supplies for stock purpose.
(ii) “Purpose” for direct issue to work (here enter full name of work as given in estimate ---------------------------- for issue to Contractor__________________ on _________________
(d) Date of written order to commence supplies
(e) Date of actual completion of supplies and
(f) Date of measurement.
A suitable abstract should then be prepared which should collect in the case of measurement for works done the total quantities of each distinct item of work relating to each sanctioned Sub-head.
If the measurements are taken in connection with running contract a reference to the last sets of measurement if any, should and if the entire job or contract has been completed the date of completion should be duly noted against the entries in the Measurement Book and in the latter case the actual date of completion should be noted in the prescribed place.
5) All measurements should be entered neatly and directly in the Draft Measurement book at the site of the work. The entries should be made in indelible ink. The person recording the measurements will also record a dated certificate measured by me and sign his full name.
6) Measurements should be checked by Junior Engineer, Assistant Engineers or Assistant Executive Engineers and by Executive Engineer in charge of works to whom Measurement Books have been supplied for the purpose or other person specially authorised by the Administration to so.
7) No erasure are allowed, if a mistake is made it should be recorded by striking out the incorrect entry and inserting the correct one between the lines. Every such correction should be initialled and dated by responsible officer.
Entries should be recorded continuously and no blank page left or turn out any pages or space left blank inadvertently should be cancelled by diagonal lines, the cancellation being attested and dated. When any measurements are cancelled or disallowed the same must be endorsed by the dated initials of the Officer ordering the cancellation or by a reference to his orders and initialled by the officer who made the measurements the reasons for cancellation being also recorded.
8) The Divisional officer should test-check at least 10% of measurements recorded by his subordinates and accept responsibility for general correctness of the bill as a whole.
9) On completion of the abstract, the book should be submitted to the Sub-Divisional officer who after carrying out his test check should enter the works” Check and Bill” with his dated initials. The Sub-divisional clerk should then check the calculation of quantities the abstract and the bill in case of work carried out by contract and should then place the Measurement Book and the bill before the Sub-divisional officer who, after comparing them who should sign the bill and the Measurement Book all quantities should clearly traceable into the documents on which payments are made, when a bill is prepared from work or supplies measured every page containing the detailed measurements, must be invariably scored out by a diagonal red ink line when the payments is made and endorsement must be made in red ink on the abstract of measurement giving a reference to the number and date of voucher of payment.
Any corrections to calculations of rates made in the Sub-divisional or Divisional officer should be made in red ink and brought to the notice of the Sub-divisional officer or the Divisional Officer as the case may be and of the person making the original measurements, in the case of final bills payment should be deferred until the corrections have been accepted by the person making the measurements. All corrections made by the clerical staff should be ink.
10) When work, which is susceptible of measurements is carried out by the daily labour a similar plan should be adopted the quantities of work done as shown on the Muster Roll being compared with the entries in the Measurements Book before payment is authorised.

## MB FORMAT
Name of work |  | :
Order No. / Agreement No. |  | :
Name of contractor |  | :
Serial.No of this bill |  | :
Date of Commencement work |  | :
Date of actual completion of work |  | :
Date of Measurements: XX.XX.XXXX
Item No | Details of Actual measurments/ Particulars | Number | Length | Width | Depth | Qty | Remarks
1

## MB - Abs- FORMAT
Name of work |  |  | :
Order No. / Agreement No. |  |  | :
Name of contractor |  |  | :
Serial.No of this bill |  |  | :
Date of Commencement work |  |  | :
Date of actual completion of work |  |  | :
Date of Abstract: xx.xx.xxxx
ABSTRACT
Item No | Details of Actual measurments/ Particulars |  | Qty | Unit | Rate | Amount (Rs)
1
B/F Page No.XX CMB XXXX
Total
2
B/F Page No.XX CMB XXXX
Total
Total value of work done till date
Deduct value of work done up to previous bill
Net value of work done since previous bill
Add secured advance , if any
Total
Recoveries
SD to be recovered in this bill
Income Tax @ 2%
ST @ 2%
Mobilization / Hypathication Advance
Electricity consumption charges
Water consumption chasrges
Other recoveries, if any
Total recoveries
Net amount payable to the agency
Certificate

## Dept. ABS (hidden)
Bill of Quantities (BOQ)
NAME OF WORK
Agreement No:-
Name of the Contractor :-
Serial No of the bill :-
Date of commencement work :-
DUE Date of completion of work :-
SL.NO | Description of Items | Qty | Unit | Rate | Upto date Amount | Upto previous Bill | Since Previous Bill